## Sheet1
Date (mm/dd/yy) | Module | Change Done by | Bug No. | Reason for Change | Change done | Database objects modified | Application Objects modified | Comment/verification Date | Testing Comment
2011-07-08 | Sap Integration | Pankaj Dhingra | None | Number of back days check removed from MOD,Invoice was of 20 Character so increase the length of the invoiceNumber column | Done | PrcInsertPrimarySalesInfoMODSapUploadForGfive, PrcInsertPrimarySalesInfoMODSapUpload,tvpPrimarySalesSapMOD | None
2011-07-11 | Sap Integration | Pankaj Dhingra | None | Requirement changed now client will send us the file in .xls format, and this change will effect the manuall upload files screen now from here user will be able to upload the file having extension .xls only | Done | None | UploadFile.cs,SapIntegration.cs,OpenXMLExcel.cs
2011-07-12 | Sap Integration | Pankaj Dhingra | None | P1SalesReturn invoice Changes which is defined in the basecamp | Done | PrcInsertPrimarySalesInfoMODSapUploadForGfive, PrcInsertPrimarySalesInfoMODSapUpload | None
2011-07-12 | Sap Integration | Pankaj Dhingra,Pardeep Sir | None | Sap files Data had spaces | Done | None | OpenXMLExcel.cs
2011-07-12 | Sap Integration | Pankaj Dhingra,Pardeep Sir | None | Now parsing user can send the xls/xlsx file | Done | None | UploadFile.cs
2011-07-12 | Global | Pankaj Dhingra,Pardeep Sir | None | Function for converting xls file to xlsx file | Done | None | Pagebase.cs(ConvertXLStoXLSX)
2011-07-14 | Change password (password expiry) | Amit Srivastava | None | Display password expiry message,also password change reminder after login to the Sytem (check for 3 day's) | Done |  | Global.asax,Default.aspx,Change Password,ManageUser,ManageSalesChannel,Welcome.css
2011-07-18 | Sap Integration | Pankaj Dhingra | None | Ftp of Gfive was not getting connected,changes in some messages also | Done | None | Sapintegration.cs(Changed in both V1,V2)
2011-07-18 | Sap Integration | Pankaj Dhingra | 9089 | Return was taking more than the sale when sale and sales return is in the same sheet(for same invoice) | Done | None | PrcInsertPrimarySalesInfoMODSapUpload,PrcInsertPrimarySalesInfoMODSapUploadforGfive(Changed in both V1,V2)
2011-07-18 | Sap Integration | Pankaj Dhingra | 9094 | remove the condition to accepting the xls file for uploading Grn,BTM,Mod manually | Done |  | uploadFile.cs
2011-07-18 | Reports (Sales, Purchase & Stock) | Amit Srivastava | None | BCP Process Implementation for Bulk Exporting of Data | Done | PrcGetFlatPurchaseRpt,PrcGetFlatSalesRpt,PrcGetStockRptExcelbybcp | WebConfig,PageBase,DownloadSalesRpt,DownloadPurchaseRpt,DownloadStockRpt
2011-07-26 | Retailer Master | Amit Srivastava | None | Add Retaile Type and Counter ISP field in ManageRetailer & Upload Retailer Interface | Done | prcInsUpdRetailerInfo,prcInsUpdRetailerUpload | Manage Retailer ,Upload Retaler
2011-07-27 | Session Timeout Control | Amit Srivastava | None | Manage Session Timeout (Alert popup) | Done | None | MasterPage.master ,ReportPage.master
2011-09-01 | Filter is added in the organisation hierarchy | Pankaj Dhingra | None | For Fastening the speed of the search with more parameters | Done | PrcGetOrgnHierarchyInfoByParameters | ManageOrgnHierarchy.aspx,ManageOrgnHierarchy.aspx.cs,OrgHierarchyData.cs
Note on F1: Author: Detailed changes should be mentioned in comment block in database/application object
Note on G2: Author: Changes Done at Zed-Sales version1 database as well as version2 Database